## Trang_tính1
# | Screen / Function | Feature | Role | Screen/Function Description | In Charge | Planned Iteration | Actual Iteration | Final Status | Update Notes | Notes | SRS | SDS
1 | Home Page | Public | All role | Show general introduction about clinic, top 10 services, top 10 doctors, the system's specialities, and clinic's map | Khương Văn Hùng | Iteration 1 | Iteration 1 | Kept |  |  | II.1.a
2 | User Login | Common | All role | Allows the user to enter email & password to login; on this page, there are also links for user to register new information or reset the password for the case s/he forget it | Phan Trương Thảo | Iteration 1 | Iteration 1 | Kept |  |  | II.2.a | II.1
3 | User Register | Common | Guest | Allows the user to register to the system by inputing following information: full name, gender (Male, Female), email, mobile, user name, login password, confirm password; User then needs to verify by clicking the link sent via email to him/her before being able to access the system | Trần Thành Lam | Iteration 1 | Iteration 1 | Kept |  |  | II.2.b | II.2
4 | Settings List | Admin | Admin | Show the paginated list of settings (include settings' id, type, value, order, status): - The admin can filter the setting by type, status - Allow the admin to seach settings by value - The list is sortable by id, type, value, order, status - From each setting, the admin can choose to view, activate/deactivate, or edit it - The page also have the button/link that allows the admin to add new setting | Hà Hữu Việt | Iteration 1 | Iteration 2 | Kept |  |  | II.3.a | II.3
5 | Setting Details | Admin | Admin | Show detailed setting information (type, value, order, note, status), from that allow the user to add new, view or edit setting info. Those are reference information used among the system: user roles, user title (Mr, Mrs, Ms, etc), post categories, service categories, specialities,.. | Nguyễn Văn Trung | Iteration 1 | Iteration 2 | Kept |  |  | II.3.b | II.4
6 | Web Blogs List | Public | All role | Show the posts paginatedly (sorted by updated date) + the right sider with the post search box, post categories, five featured posts (thumbnail, title); Post information includes its thumbnail, title, category, post date, brief-info; the user is redirected to the Blog Details page on his/her clicking on a post, redirected to this Blogs List page if the user clicks on a post category | Trần Thành Lam | Iteration 2 | Iteration 2 | Kept |  |  | II.1.b | II.9
7 | Web Blog Details | Public | All role | Show post details (including title, author, updated date, brief info, and post content) + the right sider with the post search box, post categories, five featured posts (thumbnail, title). The Blogs List page is shown when the user clicks on a post category | Trần Thành Lam | Iteration 2 | Iteration 2 | Kept |  |  | II.1.c | II.10
8 | Forgot Password | Common | All role | The user to input his/her email to receive the reset password link - On clicking the link, the user is redirected to the page in which s/he input new password (twice) - Note that the link is only available for a specific time duration as configured in the system config file. | Phan Trương Thảo | Iteration 2 | Iteration 2 | Kept |  |  | II.2.d | II.7
9 | Change Password | Common | All role | Allows the user to change his/her password by inputting his current password as well as new password (twice) | Phan Trương Thảo | Iteration 2 | Iteration 2 | Kept |  |  | II.2.c | II.8
10 | User Profile | Common | All role | This is a pop-up screen which allows the user to edit his/her profile information, including the registered user information and the avatar image (s/he is not allowed to change the email) | Hà Hữu Việt | Iteration 2 | Iteration 2 | Kept |  |  | II.2.e | II.14
11 | Patients List | Marketing | marketing, admin | List of patients in the system (seach by name) with following columns: Id, patient name, gender, date of birth, and status | Hà Hữu Việt | Iteration 2 | Iteration 2 | Kept |  |  | II.4.d | II.15
12 | Patient Details | Marketing | marketing, admin | View details of a specific patient (chosen from the Patients List screen), from this screen: - The user can see the avatar, full name, email, gender, DOB, phone, email,status - The user can activate or deactivate a patient - The user can also choose to edit the patient information via the Patient Edit screen | Nguyễn Văn Trung | Iteration 2 | Iteration 4 | Updated |  |  | II.4.e | II.5
13 | Patient Edit | Marketing | marketing, admin | Edit Patient information, including name, gender, DOB, Phone, Address | Nguyễn Văn Trung | Iteration 2 | Iteration 4 | Updated |  |  | II.4.f | II.6
14 | Accounts List | Admin | admin | List of accounts in the system. Each account include following information: Id, Fullname, Gender, Email, Mobile, User name, Role, Status From this screen, user can search accounts by full name, email, mobile or user name; user can also filter accounts by role, status; beside, user can change the role or status of each account | Đinh Thị Tươi | Iteration 2 | Iteration 2 | Kept |  |  | II.3.c
15 | Account Details | Admin | admin | This screen allow the admin to add/edit account information by inputting following data: avatar, fullname, gender, mobile, role, status; the following data are also shown on the page but read-only: id, email, user-name | Đinh Thị Tươi | Iteration 2 | Iteration 2 | Kept |  |  | II.3.d
16 | Doctors List | Marketing | marketing, admin | List of doctors in the system: - Shown columns: Id, doctor name, gender, speciality, Status - The user can search the doctors by name, filters them by gender & speciality | Khương Văn Hùng | Iteration 2 | Iteration 3 | Kept |  |  | II.4.a | II.11
17 | Doctor Details | Marketing | marketing, admin | View details of a specific doctor (chosen from the Doctors List screen); - The following information of the doctor is shown: name, Role, gender, DOB, Phone, Email, Status, Description - From this screen, the user can alos activate or deactivate a doctor + view his/her appointments + view feedbacks (both rate & comments) about him/her - The user can also choose to edit the doctor information via the Doctor Edit screen | Khương Văn Hùng | Iteration 2 | Iteration 3 | Updated | Update appointment list, patient feedback |  | II.4.b | II.12
18 | Doctor Edit | Marketing | marketing, admin | Edit doctor information which include: name, gender, DOB, Phone, doctor role, speciality, description | Khương Văn Hùng | Iteration 2 | Iteration 3 | Updated | separate the edit page from details and validate the fields |  | II.4.c | II.13
19 | Web Doctors List | Public | All role | List of doctors in the system: - Shown information of each doctor: avatar, role, speciality, rated star, and number of feedbacks - User can filter by gender & speciality; sort by rating, popular, latest, consulting fee - User can choose to view Doctor Details or Book Doctor | Phan Trương Thảo | Iteration 3 | Iteration 3 | Kept |  |  | II.1.d | II.22
20 | Web Doctor Details | Public | All role | View doctor's overview information (like in the list above), the profile description, and the patients' reviews (each include patient avatar, patient name, review date, rated star and patient's comment) | Phan Trương Thảo | Iteration 3 | Iteration 3 | Kept |  |  | II.1.e | II.23
21 | Web Services List | Public | All role | List of services in the system: - Shown information for each service include: title, category, rated star, number of feedbacks, service fee and description - User can search by name; filter by speciality; sort by the fee or the name | Hà Hữu Việt | Iteration 3 | Iteration 3 | Kept |  |  | II.1.f | II.27
22 | Web Service Details | Public | All role | View the details of the chosen service, including the introduction information (title, category, rated star, number of feedbacks, related services), overall description, and the reviews from patients (filtered by the rated star) | Hà Hữu Việt | Iteration 3 | Iteration 3 | Kept |  |  | II.1.g | II.28
23 | Appointments List | Staff | staff, admin | View list of appointments in the system, which include following columns: Id, Patient Name, Doctor Name, Time, Status. From this, the user can filter the list by the doctor name and/or status The admin can see all the appointments while the staff can only see his/her in-charged appointments | Khương Văn Hùng | Iteration 3 | Iteration 3 | Kept |  |  | II.5.a | II.24
24 | Appointment Details | Staff | staff, admin | View details of a specific appointment (chosen from the Appointments list) which include: - Patent information: avatar, name, mobile, gender, date of birth - Doctor information: avatar, name, mobile, gender, speciality, - Appointment information: date, time, status, description, in-charged staff On this screen, user can input/edit the consulting fee and change appointment status from Pending to Assigned or Cancelled; ; the admin can change the in-charged staff to a specific staff | Khương Văn Hùng | Iteration 3 | Iteration 3 | Kept |  |  | II.5.b | II.25
25 | Reservations List | Staff | staff, admin | View list of reservations in the system, which include following columsn: Id, patient name, service name, time, status; From this, user can filter the list by the service name and/or status The admin can see all the appointments while the staff can only see his/her in-charged reservations | Khương Văn Hùng | Iteration 3 | Iteration 3 | Kept |  |  | II.5.c | II.26
26 | Reservation Details | Staff | staff, admin | View details of a specific reservation (chosen from the Reservations list) which include: - Patent information: avatar, name, mobile, gender, date of birth - Service information: name, type, price - Reservation information: date, time, status, in-charged staff, description On this screen, the user can also see the detailed information of the patent as well as the booked service; the admin can change the in-charged staff to a specific staff | Đinh Thị Tươi | Iteration 3 | Iteration 3 | Kept |  |  | II.5.d | II.29
27 | Services List | Marketing | marketing, admin | List of services (paginatedly) in the system: - show following columns: id, title, category, price, status, action (edit, activate/deactivate) - search by name, filter by category - from this page, user can choose to add new or edit a service (the Service Details page is called); the user can also double click on a service to see the feedbacks on the service from patients (via the Service Feedbacks page) | Đinh Thị Tươi | Iteration 3 | Iteration 3 | Kept |  |  | II.4.g | II.30
28 | Service Details | Marketing | marketing, admin | Show detailed service information (title, category, price, thumbnail, status, description), from that allow the user to add new, view or edit service information. | Nguyễn Văn Trung | Iteration 3 | Iteration 3 | Kept |  |  | II.4.h | II.18
29 | Service Feedbacks | Marketing | marketing, admin | View feedbacks from patients to the service. Each feedback include following information: patient avatar, patient name, rated start and comments. The data list is shorted by the feedback date/time (the latest feedback is on the top of the list) | Nguyễn Văn Trung | Iteration 3 | Iteration 3 | Kept |  |  | II.4.j | II.19
30 | Blogs List | Marketing | marketing, admin | Show the paginated list of posts (include posts' id, thumbnail, title, category, author, featured, and status information): - The user can filter the post by category, author, status; also the user can search the post by title - The list can be sortable by title, category, author, featured, or status - The page also have the button/link that allows the user to add new or choose to view/update/show/hide an existing post | Trần Thành Lam | Iteration 3 | Iteration 3 | Kept |  |  | II.4.i | II.20
31 | Blog Details | Marketing | marketing, admin | Show detailed post information (thumbnail, category, title, brief information, content, flag to turn the featurning on/off, status), from that allow the user to input new post information, view or edit existing post information | Trần Thành Lam | Iteration 3 | Iteration 3 | Kept |  |  | II.4.l | II.21
32 | User Authorization | Common |  | This is authorization mechanism in the system, including the specify the user's role, his/her authorized page links (building the displayed menu items and preventing unauthorized access via enter the links directly). The scope of this function also includes building the header, footer, the main function menu (for both Admin and NonAdmin parts) | Phan Trương Thảo | Iteration 4 | Iteration 4 | Kept
33 | Dashboard | Admin | admin | Show: - Graphs & Statistics of Doctors, Patients, Appointments, and Revenue - List of today related appointments (Patient name, doctor name, date/time, Status) | Khương Văn Hùng | Iteration 4 | Iteration 4 | Kept |  | II.3.e | II.3.e | II.33
34 | My Appointments | Doctor | doctor | View doctor's list of assigned appointments paginatedly which includes following column: Id, patient name, patient Id, appointment date/time, Status. From this screen, the user can choose to view detailed information of the appointment (via the My Appointment Details page) The data is shorted by the appointment date/time (the latest one is on the top) | Hà Hữu Việt | Iteration 4 | Iteration 4 | Kept |  | II.6.c | II.6.c | II.36
35 | My Appointment Details | Doctor | doctor | View detailed information of the appointment. On this form, the doctor is allow to change the appointment status from Assigned to Completed | Hà Hữu Việt | Iteration 4 | Iteration 4 | Kept |  | II.6.d | II.6.d | II.37
36 | My Patients | Doctor | doctor | View list of doctor's patients. Each patient includes following information: avatar, name, last booking date, date of birth, email, phone | Nguyễn Văn Trung | Iteration 4 | Iteration 4 | Kept |  | II.6.a | II.6.a | II.30
37 | My Patient Details | Doctor | doctor | View detailed information of the doctor's patient (name, email, mobile, gender, date of birth) along with the list of appointments with him/her | Nguyễn Văn Trung | Iteration 4 | Iteration 4 | Kept |  | II.6.b | II.6.b | II.31
38 | My Feedbacks | Doctor | doctor | View feedbacks from patients to the doctor. Each feedback include following information: patient avatar, patient name, rated start and comments; The data list is shorted by the feedback date/time (the latest feedback is on the top of the list) | Phan Trương Thảo | Iteration 4 | Iteration 4 | Kept |  | II.6.e | II.6.e | II.32
39 | Book Appointment | Patient | patient | This screen allows user to see his current information (name, email, phone), the to-be-booked doctor information (avatar, name, rated star, number of feebacks) and input the booking details (date, time, description), from that user can book an appointment with the doctor. The newly booked appointment would be assigned automatically to the staff who has been assigned appointment or reservation for the longest time | Trần Thành Lam | Iteration 4 | Iteration 4 | Kept |  | II.7.a | II.7.a | II.34
40 | Reserve a Service | Patient | patient | This screen allows user to see his current information (name, email, phone), the to-be-reserved service information (avatar, name, rated star, number of feebacks, service fee) and input the booking details (date, time, description), from that user can book an appointment with the doctor; The newly reserved service would be assigned automatically to the staff who has been assigned appointment or reservation for the longest time | Trần Thành Lam | Iteration 4 | Iteration 4 | Kept |  | II.7.b | II.7.b | II.35
41 | Appointment History | Patient | patient | View user's list of booked appointments paginatedly which includes following column: Id, doctor avatar, doctor name, doctor Id, appointment date/time, status. The data is shorted by the appointment date/time (the latest one is on the top) | Đinh Thị Tươi | Iteration 4 | Iteration 4 | Kept |  | II.7.c | II.7.c | II.38
42 | Reservation History | Patient | patient | View list of reservations of the user, which include following columsn: Id, service name, service date/time, price, status | Đinh Thị Tươi | Iteration 4 | Iteration 4 | Kept |  | II.7.d | II.7.d | II.39
43 | Appointment,Reservation payment | Patient | Patient | This screen allows users to choose payment methods for their appointment, can choose to pay at the clinic or pay immediately through the payment service (ex: VNPay,...). | Khương Văn Hùng | Iteration 4 | Iteration 4 | New
Note on L1: ====== ID#AAAAViNgMXs KienNT (2022-02-13 14:22:10) The name of section in the SRS (software requirement specification) document
Note on M1: ====== ID#AAAAViNgMXo KienNT (2022-02-13 14:22:10) The name of section in the SDS (software design specification) document