## Trang_tính1
Title | URL | Issue ID | Assignee | Created At (UTC) | Due Date | Updated At (UTC) | Closed At (UTC) | Milestone | Labels | Related Function/Screen
Coding login | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/1 | 1 | Phan Truong Thao (FU HN) | 2022-01-13 06:08 | 2022-01-15 | 2022-01-13 06:09 | 2022-01-13 06:09 | Iteration 1 | Task,done | User Login
Login | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/2 | 2 | Phan Truong Thao (FU HN) | 2022-01-13 06:08 | 2022-01-15 | 2022-01-16 15:52 | 2022-01-16 15:52 | Iteration 1 | Task,done | User Login
Register | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/3 | 3 | Tran Thanh Lam (K15 HL) | 2022-01-13 06:10 | 2022-01-15 | 2022-01-16 15:53 | 2022-01-16 15:53 | Iteration 1 | Task,done | User Register
Home Page | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/4 | 4 | Khuong Hung | 2022-01-13 06:10 | 2022-01-15 | 2022-01-16 15:52 | 2022-01-16 15:52 | Iteration 1 | Task,done | Home Page
Forgot Password | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/5 | 5 | Khuong Hung | 2022-01-13 06:10 | 2022-01-15 | 2022-01-16 15:52 |  | Iteration 1 | Task,done | Forgot Password
Change Password | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/6 | 6 | Nguyễn Văn Trung | 2022-01-13 06:13 | 2022-01-15 | 2022-01-13 12:58 | 2022-01-13 12:58 | Iteration 1 | Task,done | Change Password
Code Java Mail | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/7 | 7 | Khuong Hung | 2022-01-13 12:57 | 2022-01-15 | 2022-01-16 15:52 | 2022-01-16 15:52 | Iteration 1 | Task,done | User Register, Change Password
Settings List | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/8 | 8 | Ha Huu Viet K15 HL | 2022-01-13 13:03 | 2022-01-15 | 2022-01-16 15:52 | 2022-01-16 15:52 | Iteration 1 | Task,done | Settings List
Setting Detail | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/9 | 9 | Nguyễn Văn Trung | 2022-01-13 13:04 | 2022-01-15 | 2022-01-16 15:52 | 2022-01-16 15:52 | Iteration 1 | Task,done | Setting Details
Complete Detailed Design Document | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/10 | 10 | Phan Truong Thao (FU HN) | 2022-01-15 08:16 | 2022-01-15 | 2022-01-16 15:52 | 2022-01-16 15:52 | Iteration 1 | Task,done
Complete SRS Document | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/11 | 11 | Khuong Van Hung (k15 HL) | 2022-01-16 04:39 | 2022-01-15 | 2022-01-16 15:51 | 2022-01-16 15:51 | Iteration 1 | Task,done
Show email in captcha page | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/12 | 12 | Khuong Hung | 2022-01-18 06:48 | 2022-01-15 | 2022-01-18 06:55 | 2022-01-18 06:55 | Iteration 1 | Task,done | Change Password
Link between login and register pages | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/13 | 13 | Khuong Hung | 2022-01-18 06:50 | 2022-01-15 | 2022-01-18 06:55 | 2022-01-18 06:55 | Iteration 1 | Task,done | User Register, Change Password
Connection home and login | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/14 | 14 | Phan Truong Thao (FU HN) | 2022-01-18 06:51 | 2022-01-15 | 2022-01-18 06:55 | 2022-01-18 06:55 | Iteration 1 | Task,done | User Login
Translate some missing words | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/15 | 15 | Phan Truong Thao (FU HN) | 2022-01-18 06:52 | 2022-01-15 | 2022-01-18 06:54 | 2022-01-18 06:54 | Iteration 1 | Task,done | Defect
Contact Page | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/16 | 16 | Khuong Hung | 2022-01-18 06:52 | 2022-01-15 | 2022-01-18 06:54 | 2022-01-18 06:54 | Iteration 1 | Task,done | Home Page
Fix missing information register | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/17 | 17 | Tran Thanh Lam (K15 HL) | 2022-01-18 06:53 | 2022-01-15 | 2022-01-18 06:54 | 2022-01-18 06:54 | Iteration 1 | Task,done | User Register
Check input information for registration and login | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/18 | 18 | Khuong Hung | 2022-01-18 06:53 | 2022-01-15 | 2022-01-18 06:54 | 2022-01-18 06:54 | Iteration 1 | Task,done | User Register, Login
Password encoding | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/19 | 19 | Khuong Hung | 2022-01-18 06:54 | 2022-01-15 | 2022-01-18 06:54 | 2022-01-18 06:54 | Iteration 1 | Task,done | User Register, Login
Web Blogs List | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/20 | 20 | Tran Thanh Lam (K15 HL) | 2022-01-19 16:54 | 2022-01-24 | 2022-02-13 14:14 | 2022-02-13 14:14 | Iteration 2 | Task,done | Web Blogs List
Web Blog Details | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/21 | 21 | Tran Thanh Lam (K15 HL) | 2022-01-19 16:55 | 2022-01-24 | 2022-02-13 14:14 | 2022-02-13 14:14 | Iteration 2 | Task,done | Web Blog Details
Forgot Password | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/22 | 22 | Khuong Hung | 2022-01-19 16:56 | 2022-01-24 | 2022-02-13 14:14 | 2022-02-13 14:14 | Iteration 2 | Task,done | Forgot Password
Change Password | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/23 | 23 | Phan Truong Thao (FU HN) | 2022-01-19 16:57 | 2022-01-24 | 2022-02-13 14:14 | 2022-02-13 14:14 | Iteration 2 | Task,done | Change Password
User Profile | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/24 | 24 | Ha Huu Viet K15 HL | 2022-01-19 16:58 | 2022-01-24 | 2022-02-13 14:14 | 2022-02-13 14:14 | Iteration 2 | Task,done | User Profile
Patients List | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/25 | 25 | Ha Huu Viet K15 HL | 2022-01-19 16:56 | 2022-01-24 | 2022-02-13 14:14 | 2022-02-13 14:14 | Iteration 2 | Task,done | Patients List
Patient Details | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/26 | 26 | Khuong Hung | 2022-01-19 16:56 | 2022-01-24 | 2022-02-13 14:14 | 2022-02-13 14:14 | Iteration 2 | Task,done | Patient Details
Doctors List | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/27 | 27 | Khuong Hung | 2022-01-19 16:56 | 2022-01-24 | 2022-02-13 14:14 | 2022-02-13 14:14 | Iteration 2 | Task,done | Doctors List
Doctor Details | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/28 | 28 | Khuong Hung | 2022-01-19 17:01 | 2022-01-24 | 2022-02-13 14:14 | 2022-02-13 14:14 | Iteration 2 | Task,done | Doctor Details
Doctor Edit | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/29 | 29 | Khuong Hung | 2022-01-19 17:02 | 2022-01-24 | 2022-02-13 14:13 | 2022-02-13 14:13 | Iteration 2 | Task,done | Doctor Edit
Write document SRS | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/30 | 30 | Phan Truong Thao (FU HN) | 2022-01-20 06:07 | 2022-01-24 | 2022-02-13 14:13 | 2022-02-13 14:13 | Iteration 2 | Task,done | Doctor Edit
Patient Edit | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/31 | 31 | Nguyễn Văn Trung | 2022-01-20 06:07 | 2022-01-24 | 2022-02-13 14:13 | 2022-02-13 14:13 | Iteration 2 | Task,done | Patient Edit
Write document Design Detail | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/32 | 32 | Phan Truong Thao (FU HN) | 2022-01-20 06:08 | 2022-01-24 | 2022-02-13 14:13 | 2022-02-13 14:13 | Iteration 2 | Task,done | Doctor Details
write document SRS inter 3 | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/33 | 33 | Khuong Hung | 2022-02-10 06:16 | 2022-01-24 | 2022-02-13 14:13 | 2022-02-13 14:13 | Iteration 2 | Task,done
write document SDS intern 3 | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/34 | 34 | Khuong Hung | 2022-02-10 06:16 | 2022-01-24 | 2022-02-13 14:13 | 2022-02-13 14:13 | Iteration 2 | Task,done
coding intern 3 | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/35 | 35 | Khuong Hung | 2022-02-10 06:27 | 2022-01-24 | 2022-02-13 14:13 | 2022-02-13 14:13 | Iteration 2 | Task,done
Code Appointments List | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/36 | 36 | Khuong Hung | 2022-02-15 06:08 | 2022-02-20 | 2022-03-01 05:53 | 2022-03-01 05:53 | Iteration 3 | Task,done | Appointments List
Write Appointments List SRS | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/37 | 37 | Khuong Hung | 2022-02-15 06:09 | 2022-02-20 | 2022-03-01 05:53 | 2022-03-01 05:53 | Iteration 3 | Task,done | Appointments List
Write Appointments List SDS | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/38 | 38 | Khuong Hung | 2022-02-15 06:09 | 2022-02-20 | 2022-03-01 05:53 | 2022-03-01 05:53 | Iteration 3 | Task,done | Appointments List
Code Appointment Details | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/39 | 39 | Khuong Hung | 2022-02-15 06:11 | 2022-02-20 | 2022-03-01 05:53 | 2022-03-01 05:53 | Iteration 3 | Task,done | Appointment Details
Write Appointment Details SRS | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/40 | 40 | Khuong Hung | 2022-02-15 06:11 | 2022-02-20 | 2022-03-01 05:53 | 2022-03-01 05:53 | Iteration 3 | Task,done | Appointment Details
Write Appointment Details SDS | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/41 | 41 | Khuong Hung | 2022-02-15 06:11 | 2022-02-20 | 2022-03-01 05:53 | 2022-03-01 05:53 | Iteration 3 | Task,done | Appointment Details
Code Reservations List | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/42 | 42 | Khuong Hung | 2022-02-15 06:12 | 2022-02-20 | 2022-03-01 05:54 | 2022-03-01 05:54 | Iteration 3 | Task,done | Reservations List
Write Reservations List SRS | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/43 | 43 | Khuong Hung | 2022-02-15 06:12 | 2022-02-20 | 2022-03-01 05:54 | 2022-03-01 05:54 | Iteration 3 | Task,done | Reservations List
Write Reservations List SDS | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/44 | 44 | Khuong Hung | 2022-02-15 06:13 | 2022-02-20 | 2022-03-01 05:54 | 2022-03-01 05:54 | Iteration 3 | Task,done | Reservations List
Write document SRS Web Doctor Details | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/45 | 45 | Phan Truong Thao (FU HN) | 2022-02-17 06:14 | 2022-02-20 | 2022-03-01 05:52 | 2022-03-01 05:52 | Iteration 3 | Task,done | Reservations List
write document SRS Web Doctors List | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/46 | 46 | Phan Truong Thao (FU HN) | 2022-02-17 06:15 | 2022-02-20 | 2022-03-01 05:51 | 2022-03-01 05:51 | Iteration 3 | Task,done | Web Doctors List
write document SDS Web Doctor Details | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/47 | 47 | Phan Truong Thao (FU HN) | 2022-02-17 06:16 | 2022-02-20 | 2022-03-01 05:52 | 2022-03-01 05:52 | Iteration 3 | Task,done | Web Doctors List
write document SDS Web Doctors List | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/48 | 48 | Phan Truong Thao (FU HN) | 2022-02-17 06:18 | 2022-02-20 | 2022-03-01 05:50 | 2022-03-01 05:50 | Iteration 3 | Task,done | Web Doctors List
Write SRS Document Blog List (Marketing) | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/49 | 49 | Tran Thanh Lam (K15 HL) | 2022-02-17 06:49 | 2022-02-20 | 2022-03-01 05:54 | 2022-03-01 05:54 | Iteration 3 | Task,done | Blog List
Write SRS Document Blog Detail (Marketing) | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/50 | 50 | Tran Thanh Lam (K15 HL) | 2022-02-17 06:50 | 2022-02-20 | 2022-03-01 05:53 | 2022-03-01 05:53 | Iteration 3 | Task,done | Blog Detail
Write Design Document Blog List (Marketing) | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/51 | 51 | Tran Thanh Lam (K15 HL) | 2022-02-17 06:51 | 2022-02-20 | 2022-03-01 05:53 | 2022-03-01 05:53 | Iteration 3 | Task,done | Blog List
Write Design Document Blog Detail (Marketing) | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/52 | 52 | Tran Thanh Lam (K15 HL) | 2022-02-17 06:51 | 2022-02-20 | 2022-03-01 05:53 | 2022-03-01 05:53 | Iteration 3 | Task,done | Blog Detail
Code Blog List (Marketing) | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/53 | 53 | Tran Thanh Lam (K15 HL) | 2022-02-17 06:52 | 2022-02-20 | 2022-03-01 05:53 | 2022-03-01 05:53 | Iteration 3 | Task,done | Blog List
Code Blog Detail (Marketing) | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/54 | 54 | Tran Thanh Lam (K15 HL) | 2022-02-17 06:53 | 2022-02-20 | 2022-03-01 05:53 | 2022-03-01 05:53 | Iteration 3 | Task,done | Blog Detail
Write document SRS Service Details | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/55 | 55 | Khuong Hung | 2022-02-17 06:55 | 2022-02-20 | 2022-02-17 06:55 | 2022-02-17 06:55 | Iteration 3 | Task,done | Service Details
Write document SRS Service Details | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/56 | 56 | Nguyễn Văn Trung | 2022-02-17 06:56 | 2022-02-20 | 2022-03-01 05:54 | 2022-03-01 05:54 | Iteration 3 | Task,done | Service Details
coding Web Doctors List | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/57 | 57 | Phan Truong Thao (FU HN) | 2022-02-17 06:56 | 2022-02-20 | 2022-03-01 05:52 | 2022-03-01 05:52 | Iteration 3 | Task,done | Web Doctors List
Write document SRS Service Feedbacks | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/58 | 58 | Nguyễn Văn Trung | 2022-02-17 06:58 | 2022-02-20 | 2022-03-01 05:53 | 2022-03-01 05:53 | Iteration 3 | Task,done | Web Doctors List
Write Design Document Service Details | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/59 | 59 | Nguyễn Văn Trung | 2022-02-17 06:58 | 2022-02-20 | 2022-03-01 05:52 | 2022-03-01 05:52 | Iteration 3 | Task,done | Web Doctors List
Code Web Services List | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/60 | 60 | Khuong Hung | 2022-02-17 06:58 | 2022-02-20 | 2022-03-01 05:52 | 2022-03-01 05:52 | Iteration 3 | Task,done | Services List
Write Design Document Service Feedbacks | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/61 | 61 | Nguyễn Văn Trung | 2022-02-17 07:00 | 2022-02-20 | 2022-03-01 05:52 | 2022-03-01 05:52 | Iteration 3 | Task,done | Service Feedbacks
coding Web Doctor Details | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/62 | 62 | Phan Truong Thao (FU HN) | 2022-02-17 07:01 | 2022-02-20 | 2022-03-01 05:50 | 2022-03-01 05:50 | Iteration 3 | Task,done | Web Doctor Details
Code Service Details | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/63 | 63 | Nguyễn Văn Trung | 2022-02-17 07:01 | 2022-02-20 | 2022-03-01 05:52 | 2022-03-01 05:52 | Iteration 3 | Task,done | Service Details
Write Web Service Details SDS | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/64 | 64 | Ha Huu Viet K15 HL | 2022-02-17 07:01 | 2022-02-20 | 2022-03-01 05:52 | 2022-03-01 05:52 | Iteration 3 | Task,done | Service Details
Write Web Service Details SRS | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/65 | 65 | Ha Huu Viet K15 HL | 2022-02-17 07:01 | 2022-02-20 | 2022-03-01 05:52 | 2022-03-01 05:52 | Iteration 3 | Task,done | Service Details
Code Service Feedbacks | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/66 | 66 | Nguyễn Văn Trung | 2022-02-17 07:02 | 2022-02-20 | 2022-03-01 05:52 | 2022-03-01 05:52 | Iteration 3 | Task,done | Service Feedbacks
Code Web Service Details | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/67 | 67 | Ha Huu Viet K15 HL | 2022-02-17 07:03 | 2022-02-20 | 2022-03-01 05:51 | 2022-03-01 05:51 | Iteration 3 | Task,done | Service Feedbacks
Write Web Services List SDS | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/68 | 68 | Ha Huu Viet K15 HL | 2022-02-17 07:04 | 2022-02-20 | 2022-03-01 05:51 | 2022-03-01 05:51 | Iteration 3 | Task,done | Web Services List
Write Web Services List SRS | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/69 | 69 | Ha Huu Viet K15 HL | 2022-02-17 07:04 | 2022-02-20 | 2022-03-01 05:51 | 2022-03-01 05:51 | Iteration 3 | Task,done | Web Services List
Write Web Services List SRS | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/70 | 70 | Dinh Thi Tuoi (K13_HN) | 2022-02-17 07:17 | 2022-02-20 | 2022-03-01 05:51 | 2022-03-01 05:51 | Iteration 3 | Task,done | Web Services List
Write Web Services List SDS | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/71 | 71 | Dinh Thi Tuoi (K13_HN) | 2022-02-17 07:18 | 2022-02-20 | 2022-03-01 05:51 | 2022-03-01 05:51 | Iteration 3 | Task,done | Web Services List
Code Reservation Details | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/72 | 72 | Dinh Thi Tuoi (K13_HN) | 2022-02-17 07:19 | 2022-02-20 | 2022-03-01 05:51 | 2022-03-01 05:51 | Iteration 3 | Task,done | Reservation Detail
Code Services List | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/73 | 73 | Dinh Thi Tuoi (K13_HN) | 2022-02-17 07:19 | 2022-02-20 | 2022-02-27 14:54 | 2022-02-27 14:54 | Iteration 3 | Task,done | Service List
Code Dashboard Admin | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/74 | 74 | Khuong Hung | 2022-03-01 05:55 | 2022-03-09 | 2022-03-23 14:26 | 2022-03-23 14:26 | Iteration 4 | Task,done | Dashboard
Write SRS Dashboard | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/75 | 75 | Khuong Hung | 2022-03-01 05:56 | 2022-03-09 | 2022-03-23 14:26 | 2022-03-23 14:26 | Iteration 4 | Task,done | Dashboard
Write SDS Dashboard | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/76 | 76 | Khuong Hung | 2022-03-01 05:57 | 2022-03-09 | 2022-03-23 14:26 | 2022-03-23 14:26 | Iteration 4 | Task,done | Dashboard
Code Book Appointment | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/77 | 77 | Tran Thanh Lam (K15 HL) | 2022-03-01 06:08 | 2022-03-09 | 2022-03-23 14:24 | 2022-03-23 14:24 | Iteration 4 | Task,done | Book Appointment
Code Reserve a Service | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/78 | 78 | Tran Thanh Lam (K15 HL) | 2022-03-01 06:09 | 2022-03-09 | 2022-03-23 14:24 | 2022-03-23 14:24 | Iteration 4 | Task,done | Reserve a Service
Write SRS Book Appointment | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/79 | 79 | Tran Thanh Lam (K15 HL) | 2022-03-01 06:10 | 2022-03-09 | 2022-03-23 14:24 | 2022-03-23 14:24 | Iteration 4 | Task,done | Reserve a Service
Write Design Book Appointment | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/80 | 80 | Tran Thanh Lam (K15 HL) | 2022-03-01 06:11 | 2022-03-09 | 2022-03-23 14:24 | 2022-03-23 14:24 | Iteration 4 | Task,done | Book Appointment
Write Design Reserve a Service | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/81 | 81 | Tran Thanh Lam (K15 HL) | 2022-03-01 06:11 | 2022-03-09 | 2022-03-23 14:24 | 2022-03-23 14:24 | Iteration 4 | Task,done | Reserve a Service
Write Design Book Appointment | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/82 | 82 | Tran Thanh Lam (K15 HL) | 2022-03-01 06:12 | 2022-03-09 | 2022-03-23 14:23 | 2022-03-23 14:23 | Iteration 4 | Task,done | Book Appointment
Write SRS User Authorization | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/83 | 83 | Phan Truong Thao (FU HN) | 2022-03-03 06:05 | 2022-03-09 | 2022-03-23 14:26 | 2022-03-23 14:26 | Iteration 4 | Task,done | User Authorization
Write SRS My Feedbacks | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/84 | 84 | Phan Truong Thao (FU HN) | 2022-03-03 06:06 | 2022-03-09 | 2022-03-23 14:25 | 2022-03-23 14:25 | Iteration 4 | Task,done | My Feedbacks
Write SDS My Feedbacks | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/85 | 85 | Phan Truong Thao (FU HN) | 2022-03-03 06:07 | 2022-03-09 | 2022-03-23 14:25 | 2022-03-23 14:25 | Iteration 4 | Task,done | My Feedbacks
write SDS User Authorization | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/86 | 86 | Phan Truong Thao (FU HN) | 2022-03-03 06:09 | 2022-03-09 | 2022-03-23 14:25 | 2022-03-23 14:25 | Iteration 4 | Task,done | User Authorization
code User Authorization | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/87 | 87 | Phan Truong Thao (FU HN) | 2022-03-03 06:09 | 2022-03-09 | 2022-03-23 14:25 | 2022-03-23 14:25 | Iteration 4 | Task,done | User Authorization
code My Feedbacks | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/88 | 88 | Phan Truong Thao (FU HN) | 2022-03-03 06:09 | 2022-03-09 | 2022-03-23 14:25 | 2022-03-23 14:25 | Iteration 4 | Task,done | My Feedbacks
Write SRS My Patients | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/89 | 89 | Nguyễn Văn Trung | 2022-03-03 06:14 | 2022-03-09 | 2022-03-23 14:25 | 2022-03-23 14:25 | Iteration 4 | Task,done | My Patients
Write SRS My Patient Details | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/90 | 90 | Nguyễn Văn Trung | 2022-03-03 06:15 | 2022-03-09 | 2022-03-23 14:25 | 2022-03-23 14:25 | Iteration 4 | Task,done | My Patient Details
Code My Patient | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/91 | 91 | Nguyễn Văn Trung | 2022-03-03 06:16 | 2022-03-09 | 2022-03-23 14:25 | 2022-03-23 14:25 | Iteration 4 | Task,done | My Patients
Code My Patient Details | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/92 | 92 | Nguyễn Văn Trung | 2022-03-03 06:16 | 2022-03-09 | 2022-03-23 14:24 | 2022-03-23 14:24 | Iteration 4 | Task,done | My Patient Details
Write SDS My Patients | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/93 | 93 | Nguyễn Văn Trung | 2022-03-03 06:17 | 2022-03-09 | 2022-03-23 14:24 | 2022-03-23 14:24 | Iteration 4 | Task,done | My Patients
Write SDS My Patient Details | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/94 | 94 | Nguyễn Văn Trung | 2022-03-03 06:18 | 2022-03-09 | 2022-03-23 14:24 | 2022-03-23 14:24 | Iteration 4 | Task,done | My Patient Details
Code Payment | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/95 | 95 | Khuong Hung | 2022-03-03 06:18 | 2022-03-09 | 2022-03-23 14:24 | 2022-03-23 14:24 | Iteration 4 | Task,done | Payment
Write SRS Payment | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/96 | 96 | Khuong Hung | 2022-03-03 06:18 | 2022-03-09 | 2022-03-23 14:23 | 2022-03-23 14:23 | Iteration 4 | Task,done | Payment
Write SDS Payment | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/97 | 97 | Khuong Hung | 2022-03-03 06:18 | 2022-03-09 | 2022-03-23 14:23 | 2022-03-23 14:23 | Iteration 4 | Task,done | Payment
Clean UI | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/98 | 98 | Khuong Hung | 2022-03-13 06:18 | 2022-03-14 | 2022-03-23 14:27 | 2022-03-23 14:27 | Iteration 5 | Task,done
Add Complete status | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/99 | 99 | Khuong Hung | 2022-03-13 06:18 | 2022-03-14 | 2022-03-23 14:28 | 2022-03-23 14:28 | Iteration 5 | Task,done
Code Account List function (Admin) | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/101 | 101 | Dinh Thi Tuoi (K13_HN) | 2022-01-19 16:54 | 2022-01-24 | 2022-03-23 15:19 | 2022-03-23 15:17 | Iteration 2 | Task,done | Account List
Code Account Details (Admin) | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/102 | 102 | Dinh Thi Tuoi (K13_HN) | 2022-01-19 16:54 | 2022-01-24 | 2022-03-23 15:18 | 2022-03-23 15:18 | Iteration 2 | Task,done | Account Details
Write SRS Account List | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/103 | 103 | Dinh Thi Tuoi (K13_HN) | 2022-01-19 16:54 | 2022-01-24 | 2022-03-23 15:20 | 2022-03-23 15:20 | Iteration 2 | Task,done | Account List
Write SRS Account detail | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/104 | 104 | Dinh Thi Tuoi (K13_HN) | 2022-01-19 16:54 | 2022-01-24 | 2022-03-23 15:21 | 2022-03-23 15:21 | Iteration 2 | Task,done | Account Details
Write SDS Account list and Account Detail of Admin | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/105 | 105 | Dinh Thi Tuoi (K13_HN) | 2022-01-19 16:54 | 2022-01-24 | 2022-03-23 15:22 | 2022-03-23 15:22 | Iteration 2 | Task,done | Account Details, Account List
Write SRS Appointment History, Reservation History (Patient) | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/106 | 106 | Dinh Thi Tuoi (K13_HN) | 2022-03-03 06:17 | 2022-03-09 | 2022-03-23 16:39 | 2022-03-23 16:39 | Iteration 4 | Task,done | Appointment History, Reservation Histor
Write SDS Reservation History, Appointment History (Patient) | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/107 | 107 | Dinh Thi Tuoi (K13_HN) | 2022-03-03 06:17 | 2022-03-09 | 2022-03-23 16:39 | 2022-03-23 16:39 | Iteration 4 | Task,done | Appointment History, Reservation Histor
Code Appointment History (patient) | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/108 | 108 | Dinh Thi Tuoi (K13_HN) | 2022-03-03 06:17 | 2022-03-09 | 2022-03-23 16:40 | 2022-03-23 16:40 | Iteration 4 | Task,done | Appointment History
Code Reservation History (Patient) | https://gitlab.com/fu-swp/spring22/se1516-net_swp391/g3/-/issues/109 | 109 | Dinh Thi Tuoi (K13_HN) | 2022-03-03 06:17 | 2022-03-09 | 2022-03-23 16:41 | 2022-03-23 16:41 | Iteration 4 | Task,done | Reservation History